## Sheet1
[6 empty] | Total Tasks | 38
| Team - Ctrl-Pay |  |  |  |  | Total Story Points | 196
Task Name | User Story | Acceptance Criteria | Story Point | Assignee | Status
Phase 1: Requirements & Design
Gather Business Requirements & Create SRS | As a product owner, I want to gather business requirements and create an SRS document so that the project scope is clearly defined. | Business requirements gathered; SRS document created and approved. | 5 | Faisal_45517457/Jahanvi-Andey | Completed
Project Planning & Task Division | As a project manager, I want to plan the project and divide tasks among the team so that deadlines are set and responsibilities are clear. | Project plan created; tasks divided; deadlines set. | 3 | GuggilamKrishnaSree / AlakhMathur / Jahanvi-Andey / Faisal_45517457 | Completed
Database Schema Design | As a system architect, I want database schemas defined so that payment, account, validation, and user data can be persisted correctly. | Database tables created; relationships defined; schema reviewed and merged. | 5 | GuggilamKrishnaSree / AlakhMathur | Completed
Frontend Initial Design | As a user, I want a frontend interface so that I can interact with payment features visually. | Frontend application created; basic screens available; backend integration started. | 8 | Jahanvi-Andey | Completed
Phase 2: Core Backend Development
Project Backend Skeleton Setup | As a developer, I want a Spring Boot backend skeleton so that further application features can be developed on a stable structure. | Application starts successfully; project structure created; required dependencies configured. | 3 | GuggilamKrishnaSree | Completed
Environment Configuration Setup | As a developer, I want environment-specific configurations so that the application can run across different environments. | Application properties configured; database connections work; environment profiles supported. | 3 | GuggilamKrishnaSree / AlakhMathur | Completed
Domain Models and DTO Creation | As a developer, I want domain entities and DTOs so that business logic can operate on structured objects. | Entities created for required modules; DTO conversion supported; validation annotations added where required. | 5 | GuggilamKrishnaSree / AlakhMathur | Completed
Repository / DAO Layer Implementation | As a developer, I want a repository layer so that database operations are separated from business logic. | CRUD operations implemented; SQL queries created; repositories tested. | 8 | GuggilamKrishnaSree / AlakhMathur | Completed
Account and User Module Backend | As a user, I want account and user management features so that payments can be associated with valid users/accounts. | User and account CRUD functionality implemented; services updated. | 13 | AlakhMathur | Completed
Account Creation Details Update | As a user, I want complete account creation details captured so that account information is stored correctly. | Additional account fields supported; creation flow updated. | 6 | AlakhMathur | Completed
Phase 3: Business Logic & Services
Payment Service Layer | As a developer, I want payment business logic separated into services so that controllers remain lightweight. | Payment creation, validation, status transitions implemented; service layer tested. | 8 | GuggilamKrishnaSree | Completed
Payment Controller and Exception Handling | As an API consumer, I want payment APIs with proper error responses so that failures are understandable. | REST endpoints available; global exception handling implemented; correct HTTP responses returned. | 8 | GuggilamKrishnaSree | Completed
Payment Lifecycle Management | As a payment system, I want payments to move through lifecycle states so that payment processing follows defined stages. | Payment transitions implemented; invalid transitions prevented; lifecycle APIs available. | 7 | GuggilamKrishnaSree | Completed
Validation Rule Engine Core | As a compliance user, I want payments validated against configurable rules so that invalid payments can be detected before processing. | Rule engine evaluates payment details; validation failures returned correctly; rules can be extended. | 8 | GuggilamKrishnaSree / AlakhMathur | Completed
Validation Rule Management APIs | As a compliance administrator, I want APIs to manage validation rules so that rules can be added or modified without changing application logic. | Rule creation, update, delete, and retrieval APIs available. | 8 | GuggilamKrishnaSree | Completed
Payment Filtering and Searching | As an operations user, I want to search and filter payments so that transactions can be monitored easily. | Filtering by payment attributes supported; pagination implemented. | 5 | GuggilamKrishnaSree | Completed
Update Rule Engine after account and user schema creation | As a compliance user, I want the rule engine to incorporate user and account data so that rules can validate based on account history and user profile. | Rule engine updated to access user/account schemas; new rules created for user validation; tests pass. | 5 | GuggilamKrishnaSree / AlakhMathur | To Do
Currency Converter Integration | As a user, I want a currency converter in the make payment section so that I can exchange between foreign currencies. | Currency converter added to make payment section; foreign exchange rates fetched and applied correctly. | 5 | GuggilamKrishnaSree / AlakhMathur | To Do
Multipart Form for Payments | As a user, I want a multipart form for payments so that I can submit payment details and files simultaneously. | Multipart form created; file upload supported; backend handles multipart requests successfully. | 5 | GuggilamKrishnaSree / AlakhMathur | To Do
Phase 4: Advanced Features & ML
Retry Mechanism / Advanced Features | As a payment processor, I want retry handling so that temporary failures do not permanently fail transactions. | Retry logic implemented; failed processing attempts handled correctly. | 8 | GuggilamKrishnaSree | Completed
Fraud Detection ML Model Creation | As a risk manager, I want an ML model to detect fraudulent transactions so that financial losses are minimized. | ML model trained with historical data; accuracy > 95%; API endpoint created for predictions. | 15 | Faisal_45517457 | In Progress
Implement Rate Limiting and Security Policies | As a security engineer, I want rate limiting and security policies implemented so that the APIs are protected from abuse and DDoS attacks. | Rate limiting configured for public APIs; security headers added; tests verify rate limits. | 5 | GuggilamKrishnaSree / Alakh Mathur | To Do
Integrate ML Model in rules engine | As a compliance user, I want the fraud detection ML model integrated into the rule engine so that transactions are automatically scored for fraud during processing. | ML model API called during payment validation; rules evaluate fraud score; high-risk payments blocked. | 8 | Faisal_45517457 / GuggilamKrishnaSree | To Do
Phase 5: Frontend Integration & Refinement
Frontend Completion Phase Fixes | As a user, I want stable UI behavior so that payment completion screens work correctly. | Loading/spinning issues fixed; completion flow works correctly. | 3 | GuggilamKrishnaSree | Completed
Check for UI Enhancements | As a user, I want a polished and responsive UI so that my experience is seamless across devices. | UI audited for responsiveness; accessibility improvements applied; minor visual bugs fixed. | 5 | Jahanvi-Andey | To Do
Phase 6: Testing & Quality Assurance
Dependency Issue Resolution | As a developer, I want dependency issues resolved so that the application builds successfully. | Build passes; dependency conflicts removed. | 3 | GuggilamKrishnaSree / AlakhMathur | Completed
Testing and Documentation | As a developer, I want tests and documentation so that the system can be maintained and verified. | Test cases written; project documentation updated; setup instructions available. | 5 | GuggilamKrishnaSree/ Alakh Mathur / Jahanvi-Andey / Faisal_45517457 | To Do
Testing and Test Coverage to be checked | As a developer, I want to ensure high test coverage so that the application is stable and bug-free. | Unit and integration tests written for all modules; test coverage > 80%; sonarqube reports generated. | 5 | GuggilamKrishnaSree / Alakh Mathur | To Do
Phase 7: DevOps & Production Deployment
Docker and Infrastructure Setup | As a DevOps engineer, I want containerized deployment so that the application can run consistently across environments. | Docker images created; services containerized; application runs using containers. | 8 | Alakh Mathur | To Do
Integrate Nginx and docker | As a DevOps engineer, I want Nginx configured as a reverse proxy for Docker containers so that traffic is routed securely and efficiently. | Nginx configuration created; Docker compose updated to include Nginx; traffic successfully routed to backend. | 5 | Alakh Mathur | To Do
Build CI/CD Pipeline | As a DevOps engineer, I want a CI/CD pipeline so that code changes are automatically built, tested, and deployed. | Pipeline configured (e.g., Jenkins/GitHub Actions); automated tests run on PR; successful builds deployed to staging. | 8 | Alakh Mathur | To Do